## Dashboard
PROJECT MANAGEMENT PORTFOLIO
Total Projects | 15 | Total Budget | 0
Active Projects | 8 | Spent to Date | 2365000
Completed Projects | 3 | Remaining Budget | -2365000
At Risk Projects | 2 | Budget Utilization | 0%

## Projects
PROJECT LIST
ID | Project Name | Owner | Status | Priority | Start Date | End Date | Budget | Spent | Progress %
PRJ001 | Website Redesign | Sarah Chen | In Progress | High | 2024-01-15 | 2024-06-30 | 150000 | 89000 | 65%
PRJ002 | Mobile App Development | James Wilson | In Progress | Critical | 2024-02-01 | 2024-08-31 | 250000 | 125000 | 55%
PRJ003 | CRM Implementation | Maria Garcia | Completed | Medium | 2023-09-01 | 2024-03-31 | 180000 | 175000 | 100%
PRJ004 | Data Migration | David Kim | In Progress | High | 2024-03-15 | 2024-07-15 | 95000 | 58000 | 70%
PRJ005 | Marketing Campaign | Emily Johnson | Planning | Low | 2024-05-01 | 2024-09-30 | 75000 | 5000 | 10%
PRJ006 | Infrastructure Upgrade | Michael Brown | In Progress | Critical | 2024-01-01 | 2024-05-31 | 320000 | 245000 | 80%
PRJ007 | Customer Portal | Lisa Anderson | At Risk | High | 2024-02-15 | 2024-06-15 | 125000 | 95000 | 60%
PRJ008 | Analytics Dashboard | Robert Lee | In Progress | Medium | 2024-03-01 | 2024-07-31 | 88000 | 42000 | 50%
PRJ009 | Security Audit | Jennifer Taylor | Completed | Critical | 2023-11-01 | 2024-02-28 | 65000 | 63000 | 100%
PRJ010 | Training Program | Christopher Martinez | In Progress | Low | 2024-04-01 | 2024-10-31 | 45000 | 12000 | 30%
PRJ011 | ERP Integration | Amanda White | Planning | High | 2024-06-01 | 2024-12-31 | 280000 | 15000 | 5%
PRJ012 | API Development | Daniel Harris | In Progress | Medium | 2024-02-20 | 2024-08-20 | 110000 | 67000 | 62%
PRJ013 | Cloud Migration | Michelle Clark | In Progress | Critical | 2024-01-10 | 2024-06-30 | 395000 | 285000 | 75%
PRJ014 | Mobile Optimization | Thomas Rodriguez | Completed | Low | 2023-10-15 | 2024-01-31 | 52000 | 51000 | 100%
PRJ015 | Vendor Management System | Jessica Lewis | At Risk | Medium | 2024-03-10 | 2024-07-31 | 135000 | 108000 | 68%

## Timeline
PROJECT TIMELINE
Project ID | Project Name | Start Date | End Date | Duration (Days) | Status | Days Remaining | Progress
PRJ001 | Website Redesign | 2024-01-15 | 2024-06-30 | 167 | In Progress | -648 | 65%
PRJ002 | Mobile App Development | 2024-02-01 | 2024-08-31 | 212 | In Progress | -586 | 55%
PRJ003 | CRM Implementation | 2023-09-01 | 2024-03-31 | 212 | Completed |  | 100%
PRJ004 | Data Migration | 2024-03-15 | 2024-07-15 | 122 | In Progress | -633 | 70%
PRJ005 | Marketing Campaign | 2024-05-01 | 2024-09-30 | 152 | Planning | -556 | 10%
PRJ006 | Infrastructure Upgrade | 2024-01-01 | 2024-05-31 | 151 | In Progress | -678 | 80%
PRJ007 | Customer Portal | 2024-02-15 | 2024-06-15 | 121 | At Risk | -663 | 60%
PRJ008 | Analytics Dashboard | 2024-03-01 | 2024-07-31 | 152 | In Progress | -617 | 50%
PRJ009 | Security Audit | 2023-11-01 | 2024-02-28 | 119 | Completed |  | 100%
PRJ010 | Training Program | 2024-04-01 | 2024-10-31 | 213 | In Progress | -525 | 30%
PRJ011 | ERP Integration | 2024-06-01 | 2024-12-31 | 213 | Planning | -464 | 5%
PRJ012 | API Development | 2024-02-20 | 2024-08-20 | 182 | In Progress | -597 | 62%
PRJ013 | Cloud Migration | 2024-01-10 | 2024-06-30 | 172 | In Progress | -648 | 75%
PRJ014 | Mobile Optimization | 2023-10-15 | 2024-01-31 | 108 | Completed |  | 100%
PRJ015 | Vendor Management System | 2024-03-10 | 2024-07-31 | 143 | At Risk | -617 | 68%
Formulas:
Days Remaining = IF(AND([End Date]<>"",[Status]<>"Completed"),[End Date]-TODAY(),"")

## Budget Tracking
BUDGET TRACKING
Project ID | Project Name | Allocated Budget | Spent | Remaining | Utilization % | Status
PRJ001 | Website Redesign | 150000 | 89000 | 61000 | 59.33% | Under Budget
PRJ002 | Mobile App Development | 250000 | 125000 | 125000 | 50% | Under Budget
PRJ003 | CRM Implementation | 180000 | 175000 | 5000 | 97.22% | Over Budget
PRJ004 | Data Migration | 95000 | 58000 | 37000 | 61.05% | Under Budget
PRJ005 | Marketing Campaign | 75000 | 5000 | 70000 | 6.667% | Under Budget
PRJ006 | Infrastructure Upgrade | 320000 | 245000 | 75000 | 76.56% | On Track
PRJ007 | Customer Portal | 125000 | 95000 | 30000 | 76% | On Track
PRJ008 | Analytics Dashboard | 88000 | 42000 | 46000 | 47.73% | Under Budget
PRJ009 | Security Audit | 65000 | 63000 | 2000 | 96.92% | Over Budget
PRJ010 | Training Program | 45000 | 12000 | 33000 | 26.67% | Under Budget
PRJ011 | ERP Integration | 280000 | 15000 | 265000 | 5.357% | Under Budget
PRJ012 | API Development | 110000 | 67000 | 43000 | 60.91% | Under Budget
PRJ013 | Cloud Migration | 395000 | 285000 | 110000 | 72.15% | Under Budget
PRJ014 | Mobile Optimization | 52000 | 51000 | 1000 | 98.08% | Over Budget
PRJ015 | Vendor Management System | 135000 | 108000 | 27000 | 80% | On Track
TOTAL |  | 2365000 | 1435000 | 930000 | 60.68%